## Slide 1: IMPLEMENTATION Status of “SAHAS” Global Fund Grant (2018-2021)

## Slide 2
Program Title | “SAHAS” (Strategic Augmentation of HIV/AIDS services)
Grant Name and Number | IND-H-NACO-1566
Grant Amount | US$ 102.3 million
Implementation Period | 1st Jan 2018 to 31 March 2021
Principal Recipient | The Department of Economic Affairs ( Implementation through NACO)
SAHAS Grant Details

## Slide 3
Chart: 
| NACO | Alliance India | SAATHI | CHAI | PLAN India | TISS
Sales | 0.66 | 0.13 | 0.07 | 0.026823 | 0.09 | 0.023384
HIV Grant Budget distribution ( in %)
  1. Plan India (17.38 mUSD)
  Elimination of Mother to child transmission of HIV & Syphilis-( 8.0 mUSD)
  Capacity Building of ANM, ICTC& ART Counsellors (3.4 mUSD)
  SR- TISS
  Supply Chain Management of ARV drus & testing Kits- (5.7 mUSD)
  SR – JSI, TCI Express
2. Solidarity and Action Against The HIV Infection in India (SAATHII) (10.371 mUSD)
Elimination of Mother to child transmission of HIV & Syphilis -7.0
Blended Clinical trainings (3.37 mUSD)
Technology partner –K-nomics
  3. India HIV/AIDS Alliance (20.566 mUSD)
  Access to Comprehensive Care and Support services for PLHIV
4. William J Clinton Foundation (CHAI) (3.942 mUSD)
Integrating IT & M&E systems Of NACO
“SAHAS”
Strategic Augmentation of HIV AIDS Services
National AIDS Control Organisation ( 102.3 mUSD )
Government Principal Recipient
HIV Grant Allocation 155 m USD
Non Government Principal Recipient

## Slide 4
Grant Details | Figures in mUSD
Total Grant ( Jan 2018-March 2021) | 102.3 mUSD
Disbursement made by GF (as on September 2018) | -
SAHAS Grant Status
Expenditure Current status | Figures in mUSD
Expenditure up to 30st Sept 2018 | .7
Committed Expenditure upto 31st Dec 2018 | 1.2
Total | 1.9

## Slide 5
SNo | Activity | Budget in mUSD | Actual expenditure | Current status
1 | Viral load test for routine monitoring | 41.9 | - | More than 2lakh test performed.
2 | ART drugs for treat all | 32.98 |  | Indent to CMSS given
3 | Differentiated HIV testing and ICTC infrastructure | 10.5 |  | States to augment with additional funding in next FY for implementation
4 | HIV-Hep C co infection | 5.72 |  | Leverage on National Hepatitis Programme
5 | Differentiated Care | 2.92 |  | Funds not allocated in AAP
6 | Evidence Generation for Policy Making | 2.68 |  | ongoing
Activities under SAHAS Grant :Implementer- NACO

## Slide 6
 | Activities | Total Budget (million USD) | Actual expenditure | Current status
7 | Digital Records | 2 | - | States to augment with additional funding in next FY for implementation
8 | NPMU | 1.39 | - | Offer letter to consultants is to be issued
9 | Community based testing | 0.91 | - | States to augment with additional funding in next FY for implementation
10 | Self Testing | 0.81 |  | SOPs to be drafted
Activities under SAHAS (2/2)

## Slide 7: 1. Viral load test for routine monitoring
 | Target |  | Achievement | 
 | Qty. | Amount | Qty. | Amount
Q1 | 0 | 0 | 225434 tests (as on 2.3.2019) | 
Q2 |  |  |  | 
Q3 |  |  |  | 
Q4 |  |  |  | 
Total |  |  |  | 
Qty in Lakh, Amt. in mUSD
Tests proposed for year-1- 1.25 Lakh tests, and 8.62 lakh tests in Y-2

## Slide 8: 2. ARV (TLE)- for Test and Treat
To support PLHIVs who will be newly initiated on ART (TLE) during three year period
  Yr -1- 100% support for estimated 86,648 PLHIVs
  Yr-2- 80% Support for total estimated1,16,491 newly initiated PLHIVs
  Yr-3 60% Support for total estimated 116491 newly initiated PLHIVs
Total Quantity - 4,821,884 Packs
Total Budget-32.98 MUSD
Indent has been placed with CMSS.

## Slide 9: 3. Infrastructure at ICTC
Current Status: Finance & Procurement Division has recommended for allocating Funds in GIA ( AAP) for local procurement in AAP
 | Quantity |  | 
 | Y1 | Y2 | Y3
New ICTC | 1000 | 1000 | 1000
​Domestic Refrigerators for TI |  | 1500 | 
​Ice Lined refrigerators |  | 1567 | 
​Cold Carrier (HIV Test Kit Carrier) | 4500 | ​ | 
​Walk in Cooler | 55 |  | 
​DG Set | 55 |  | 
​**Tablets | 4580 | 5552 | 
​*Routers | 767 | 5552 | 

## Slide 10: 4. HIV-Hep C co infection- 5.72 mUSD
Approx. 13 lakh PLHIVs in care to be screened and treated
NVHCP agreed to support for the drugs, confirmatory kits and Trainings.
NACO has provided their patient load data for forecasting of Drugs & Confirmatory kits and other consumables.
Budgeted amount to be reprogrammed as per programme need.

## Slide 11: 5. Differentiated Care Centres -2.9 mUSD
Fifty new centres has been proposed in Q-4 and another Fifty new centres –Q5
World Bank has agreed to provide support for HR.
Budget in AAP not allocated. However identification of centres has been prepared . Budget to be allocated to SACS in next FY AAP.

## Slide 12: 6. Evidence generation for policy change
Continuation of studies and new studies proposed for evidence generation for policy change
Budget- 2.69 mUSD
Two studies budget and protocol is under examination by GF.

## Slide 13: 7. Digitalization of Records
Proposal for procurement of Tablets for ART centres and ICTC along with routers is proposed in last quarter and first quarter of FY 19-20.
Allocation of funds in GIA ( AAP) for local procurement has been recommended.

## Slide 14: 8. NPMU
National Program Management Unit to oversight and manage smooth implementation of HIV Global Fund grant.
The Unit comprises of 4 consultants-
  Grant Program Manager
  M&E consultant
  Finance consultant
  Grant coordinator
Budget - 1.38 mUSD
Screening committee approval has been received. Offer letter to be given to the selected candidates

## Slide 15: 9. Community Based Screening (Non TI)
  List of 50 districts identified by the programme has been shared with States for Confirmation
  Allocation of Funds in GIA ( AAP) for local procurement in AAP has been recommended.
Activity Description | Y1 Unit Cost (Payment Currency) | Q4 Quantity | Q4 Cash Outflow (Grant Currency)
Demand Generation through Folk media and street plays | 20,000 | 50 | 15,385
Cold Chain Boxes for Community Navigator | 3,000 | 4,000 | 184,615
Training and dissemination workshop | 1,487,000 | 1 | 22,877
Cost of travel to Community Navigators to govt hospital for weekly disposal of used kits | 50 | 48,000 | 36,923
Tablets for field cooridnators | 6,000 | 100 | 9,231
Development of online tool for reporting by FC | 1,600,000 |  | 
Internet for tablets | 600 | 100 | 923
Salary of Field coordinator | 10,000 | 100 | 15,385
Incentive for screening | 20 | 120,000 | 36,923
Incentive for linking of reactive cases with ICTC | 100 | 6,000 | 9,231
Incentive for referral by clients | 10 | 24,000 | 3,692
Incentive for reactive referral by clients | 50 | 1,200 | 923
Community Based Testing - Cold Chain Box (Buffer at ICTC) | 3,000 | 500 | 23,077
Refrigeration units - Community Based testing |  |  | 
Cost of Hypochloride solution for disposal of used kits to Community Navigators | 50 | 48,000 | 36,923

## Slide 16: 10. HIV Self testing
  Second meeting of Technical Advisory Group on HIV self testing - 3rd Aug 2018
      Reviewed the protocol developed by ICMR-NARI, for prospective evaluation study to assess the “Accuracy (sensitivity and specificity) of self-screening for HIV-1 and HIV-2 antibody in oral fluid.
      Minutes of the meeting has been shared with TAG
      Awaiting comments from TAG on the protocol
Third meeting of Technical Advisory Group on HIV self testing to be scheduled

## Slide 17: Performance Framework (PF)
Indicator | Baseline |  | Target | Achievement
 | Year | Baseline | Sep 2018 | 
Number of people who were tested for HIV and received their results during the reporting period | 2017 | 3.4 crore |  | 3.1 crores
Percentage of HMIS or other routine reporting units submitting timely reports according to national guidelines | 2016 | 33 states | 30 | 29
Percentage of people living with HIV and on ART, who have a suppressed viral load at 12 months (<1000 copies/ml) |  |  | 70% | Not captured

## Slide 18: Challenges
Disproportionate allocation of Funds under AAP
Anticipated savings under Hep-C component
Anticipated savings due to delay in procurement

## Slide 19
Thank You..